## todo
version v250410
[5 empty] | crane | s4/s2 | DAQ | online
Main task | id | need | subtask | ETC |  |  |  |  | April | May May |  |  |  | June June June June June June June June June | [29 empty] | notes
General | [8 empty] | week 17 | week 18 | week 19 | week 20 | week 21 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
| g1 |  | define the program | [40 empty] | urgent!!! | bar: April week 17 to May May week 18
Logistic
| l1 |  | plug camera
| l2 |  | source key and triangle | bar: May May week 21
| l3 |  | buy new hard drive | bar: May May week 18
| l4 |  | decide online computer/all etch | bar: April week 17
| l5 |  | Prepare file sheets
| l6 |  | Prepare Si current monit.
| l7 |  | Prepare monitoring sh.
[5 empty] | crane | s4/s2 | DAQ | online
Main task | id | need | subtask | ETC |  |  |  |  | April week 17: April; May May week 18: May May; June June June June June June June June June 1: June June June June June June June June June | notes
Mechanics |  |  | PB, AB, CD | [5 empty] | week 19 | week 18 | week 19 | week 20 | week 21 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | cables/heavy mounting
mechanics S2 |  | AB | AB
| s2a1 |  | Finger support design | 0.5
| s2a2 |  | fetch finger cables/HV connection | 0.5 | [39 empty] | order/make new if needed
| s2a3 |  | dismount S2
| s2a4 |  | TPC S2 mount
| s2a5 | s2a1 | finger mount
| s2a6 |  | mount rack s2 | [40 empty] | 1 nim, one ISEG?, one VME
target-LYCCA preparation |  |  | PB, AB
| t1 |  | Mount the feedthrough in the new target flange. | [40 empty] | Feed through from York and Koeln | bar: May May week 18 to May May week 21
| t2 |  | Change the rod for the target leader flange. | bar: May May week 18 to May May week 21
| t3 |  | Check that the drive mechanism operates properly | bar: May May week 18 to May May week 21
| t4 |  | Make the cables from the target detectors to the Flange. | [40 empty] | Cables from Lund and York | bar: May May week 18 to May May week 21
| t5 |  | Check that the targets are available | bar: May May week 18 to May May week 21
| t6 |  | Estimate the number of tiles needed for the Pb Wall. Make sure we have sufficient | bar: May May week 18 to May May week 21
| t7 |  | vacuum test outside S4?? | bar: May May week 18 to May May week 21
mechanics S4-tracking |  | AB | PB,AB
FE | s4a1 |  | Clean the S4 area, | 0.5
|  |  | Cables for LYCCA, signals and LYCCA stop SCI-HV, start SCI-HV(where?) | 2 to 3 | [39 empty] | Need to the scheduled
|  |  | Move the LYCCA table in its final position and mount the tubes supported on the table | 0.5
|  |  | Mount the support for the target cross an the Cross it self. Perform initial alignment | 1
|  |  | Fix the table to the floor(cut the plate) | 0.5
Mark grounding points for the table and the Target NIM-bin rack
|  |  | Solder the grounding screws: table and target crate | [40 empty] | scheduled in advance
Mark the position for the Pb wall (if it is to be moved closer to the target)
|  |  | Drill new holes for the Pb wall or replace the screws from the old wall | 0.5 | [39 empty] | scheduled in advance
|  |  | Dismount the target cross and put in the Pb wall support | 0.5
|  |  | Mount the LYCCA chamber with no detectors, and the NIM-bin rack under LYCCA. Ground the rack.(add weight if needed for the table to bend the Fe plate) | 0.25
|  |  | Mount the target cross, alignment | 1.5
|  |  | Build the Pb wall, cut the tiles as needed | 1 to 3 | [39 empty] | scheduled in advance
Check the aliment
|  |  | Fix the target cross with support under the Target position | 0.5 | [39 empty] | Need to find a proper support and adjust it
|  |  | Mount the turbo pump, target leather flange and feed through flange | 0.5
Calibrate the target motor drive
|  |  | First pumping. Leak check. | 1
|  |  | Mount the new NIM and VME bins at S2/S4 | 1 to 2
HV crate for the LYCCA SCI(possible space conflict)
|  |  | Prepare the target rack(2NIM-bins) | 1 to 2 | [39 empty] | ??? just the crates or filled?
FE | s4a30 | f1 | Mount the FRS detectors at S4: TPC, MUSIC, SC41 | 1 to 2
FE | s4a31 |  | Mount slits and the S4 degrader | 1 to 2
RH | s4a32 | l1 | mount LYCCA start scintillator | 0.5 to 4
Euroball array |  |  | IK
IK, TE | me1 |  | mount-dismount the detectors
IK, TE | me2 | me1 | cable the detectors HV
SP+??? | me3 | me1 | cable the detectors signal
IK, TE | me4 |  | change the LN2 tubes day one | [40 empty] | nobody allowed in S4
IK, TE | me5 |  | change the LN2 tubes
IK, TE | me6 | me1 | mount Pb shields | [40 empty] | after calibration???
IK, TE | me7 |  | check Ge drive right side
Hector |  |  | PB
| mh1 |  | localize the pieces
| mh2 |  | design the structure
| mh3 |  | mount the structure
| mh4 |  | mount the detectors
| mh5 |  | decide the electronic crates location
| mh6 |  | mount the electronic crates/rack
| mh7 |  | cable Hector
Agata |  |  | CD
| ma1 |  | design the table
PB,SP,CD | ma2 |  | decide table/rack/electronics location | bar: April week 19 to May May week 19
| ma3 |  | prepare the cables
| ma4 |  | check the table
| ma5 |  | mount the table
| ma6 |  | mount the detector
| ma7 |  | move the VME crate and HV
| ma8 |  | cable the detector
[5 empty] | crane | s4/s2 | DAQ | online
Main task | id | need | subtask | ETC |  |  |  |  | April week 19: April; May May week 18: May May; June June June June June June June June June 1: June June June June June June June June June | notes
Detectors | [8 empty] | week 17 | week 18 | week 19 | week 20 | week 21 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
FRS
| f1 |  | decide for FRS layout | bar: April week 17 to May May week 19
| f2 |  | cable s2 finger detector
| f3 |  | decide for Music electronic | bar: April week 17 to May May week 19
| f4 | s4a30 | cable s4 FRS detector
| f5 | f4 | test cabling S2-MH
| f6 | f4 | test cabling S4-MH
| f7 |  | test detectors
| f8 |  | test music pre amp
| f9 |  | test MWPC (S2 and S4)
| f10 |  | test plastics
| f11 | ??? | cable FRS ratemeter
| f12 |  | check lookup table
| f13 |  | prepare probe P,T
| f14 |  | test probe P,T
| f15 |  | set musc shp. mit pul.
| f16 |  | tac calibration
| f30 | g1 | decide beam planning
| f31 | f30 | FRS calculation
| f32 | f31 | write short documentation
LYCCA-target |  |  | DR, PB | [40 empty] | need input from LYCCA
RH | l1 |  | Prepare the two new Scintillators for LYCCA
| l2 |  | Cable/Electronic start LYCCA scintillator
| l3 |  | Cable/Electronic stop LYCCA scintillator
| l4 |  | Cable/Electronic LYCCA
| l5 |  | Mount the target DSSSD
| l6 |  | Mount the target Diamond
| l7 |  | Mount the diamond pre-amps
| l8 |  | Cable/Electronic the DIAMOND detector
| l9 |  | Cable/Electronic the target DSSSD
| l10 |  | Test scintillator electronic
| l11 |  | test DSSD and CsI
| l12 |  | calibrate CsI and DSSD
| l13 |  | check online
| l14 |  | write short documentation
Euroball |  |  | IK, SP
| e1 |  | check lookup table | 0.5
| e2 |  | get sources
| e3 |  | set TFA | 0.5
| e4 |  | set DGF gain | 0.5
| e5 |  | DGF tau setting | 2 | [39 empty] | automatic
| e6 |  | DGF offset
| e7 |  | calibration all | 1
| e8 |  | resolution all | 0.5
| e9 |  | check DGF time reference
| e10 |  | write short documentation
Hector |  |  | FC | [40 empty] | need Franco
| h1 |  | get information and update list | bar: April week 17
Agata |  |  | CD
| a1 |  | cable AGATA
| a2 |  | check background
| a3 |  | calibrate AGATA
| a4 |  | mount shield??
| a5 |  | check online
[5 empty] | crane | s4/s2 | DAQ | online
Main task | id | need | subtask | ETC |  |  |  |  | April week 17: April; May May week 18: May May; June June June June June June June June June 1: June June June June June June June June June | notes
EDAQ |  |  | HeS, Nk, SP | [5 empty] | week 17 | week 18 | week 19 | week 20 | week 21 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Electronic and DAQ |  |  | HeS, SP, PB...
HeS, SP | el1 |  | determine architecture | [40 empty] | need input from AGATA and Hector | bar: April week 17 to May May week 19
HeS, SP, PaB, DR | el2 |  | determine layout | bar: May May week 20
SP, HeS | el3 |  | check all modules availability | bar: May May week 19
| el4 |  | buy trigger bus cable () | [40 empty] | 1 to 2 dep. of Hector
SP, HeS | el41 |  | check Gigabit ethernet connexcion | bar: May May week 20
| el42 |  | buy new PC event builder | bar: May May week 20
SP | el5 |  | agree trigger types
SP | el6 |  | ask same layout TPC | [40 empty] | online reason
SP | el7 |  | build same layout FRS crate | [40 empty] | online reason
SP | el8 |  | prepare readout FRS/TPC
HeS | el9 |  | prepare readout LYCCA/Ge | [40 empty] | Ge like last time
SeB, HeS | el10 |  | prepare readout Hector
HeS | el11 |  | prepare readout AGATA | [40 empty] | 2x bigger time step
HeS, NiK | el12 |  | prepare readout Music new/user
| el43 |  | optimize pipe size for DelEvtBuild
| el13 |  | mount VME electronic
| el14 |  | cable trigger bus
SP, HeS | el15 |  | test readout
SP | el16 |  | write short manual
| el17 |  | pedestal LYCCA
| el18 |  | pedestal Hector
| el19 |  | pedestal FRS
Trigger |  |  | SP,
| tr1 |  | design trigger circuit | [40 empty] | trigger mult Ge??
| tr2 |  | define trigger | bar: May May week 20 to May May week 21
| tr3 |  | cable trigger matrix | bar: May May week 20 to May May week 21
| tr3a |  | prepare trigger 12, 13 for delayed event build. | bar: May May week 20 to May May week 21
| tr4 |  | collect dead time cables
| tr5 |  | Cable trigger logic LYCCA
| tr6 |  | test LYCCA trigger timing
| tr7 |  | cable trigger logic Ge
| tr8 |  | cable trigger logic finger
| tr9 |  | cable trigger logic FRS-mhTDC-music-scaler | bar: June June June June June June June June June 1 to June June June June June June June June June 4
| tr10 |  | write documentation
User crate/scaler
| u1 |  | define what in scalers
| u2 |  | define what in rate meter
| u3 |  | cable scaler
| u4 |  | cable rate meter PRESPEC
| u5 |  | cable mhTDC
| u6 |  | cable music new readout
| u7 |  | write short documentation
Slow control |  |  | HeS
| sl1 |  | see Hector slow control need | bar: April week 17
| sl2 |  | see diamond slow control need | bar: April week 17
| sl3 |  | see AGATA slow control need | bar: April week 17
| sl4 |  | see Music readout slow control need | bar: April week 17
| sl5 |  | define slow control plastic
| sl6 |  | define slow control finger
| sl7 |  | define slow control diamond
| sl8 |  | update from information
PG | sl9 |  | setup slow control LYCCA
| sl10 |  | setup slow control Ge
PG, RH, HeS/SP | sl11 |  | write short documentation
Online |  |  | SP, EM, PB
SP | o1 |  | test new cracow on old data | bar: May May week 20
| o2 |  | check in need update online definition | [40 empty] | case Jurek away and no root trees
| o3 |  | test cracow on new data | [40 empty] | do not need full syst.
RH, NS | o4 |  | define GO4 for diamond | bar: April week 17 to May May week 20
RH | o5 |  | define GO4 for LYCCA | bar: April week 17 to May May week 20
FC | o7 |  | define GO4 Hector (ask them) | bar: April week 17 to May May week 20
| o8 |  | define main Go4 | [40 empty] | AGATA in???? | bar: April week 17 to May May week 20
| o9 |  | build main GO4 unpacker
| o10 |  | build main GO4 calibration
| o11 |  | combine two streams
| o12 |  | check online on data
| o13 |  | prepare small analysis routine
| o14 |  | write short documentation

## task local contact
[5 empty] | crane | s4/s2 | DAQ | online
Main task | id | need | subtask | ETC |  |  |  |  | notes
General
| g1 |  | define the program | [5 empty] | urgent!!!
Logistic
[5 empty] | crane | s4/s2 | DAQ | online
Main task | id | need | subtask | ETC |  |  |  |  | notes
Mechanics |  |  | PB, AB | [5 empty] | cables/heavy mounting
mechanics S2 |  | AB | AB
target-LYCCA preparation |  |  | PB, AB
mechanics S4-tracking |  | AB | PB,AB
Euroball array |  |  | IK
Hector |  |  | PB
Agata |  |  | CD
[5 empty] | crane | s4/s2 | DAQ | online
Main task | id | need | subtask | ETC |  |  |  |  | notes
Detectors
FRS |  |  | ??
LYCCA-target |  |  | DR, PB | [5 empty] | need input from LYCCA
Euroball |  |  | IK, SP
Hector |  |  | FC | [5 empty] | need Franco
Agata |  |  | CD, EM
[5 empty] | crane | s4/s2 | DAQ | online
Main task | id | need | subtask | ETC |  |  |  |  | notes
EDAQ |  |  | HeS, Nk, SP
Electronic |  |  | HeS, SP,
Trigger |  |  | SP,
User crate/scaler |  |  | SP
Slow control |  |  | HeS
Online |  |  | SP, EM, RH

## chartforfun
|  |  |  | FRS |  |  |  | LYCCA
| Agata | Hector | Germanium | TPC | FRS | music+ | finger | LYCCA tof | LYCCA diam | LYCCA ca
simulation
infrastruc
mechanics
mounting
cabling
testing
Front end
NIM elect
operation
Digitizer
Trigger
DAQ
online
slow control
HeS
Milano
IK,CD, PB
CD
SP??
PB, AB
Bratislava
PB, SP + expert team
KVI
Miroslav
LUND+ Koln
York
EDAQ group (NK, HeS, SP)
EM, RH, SP
HeS+Lund

## modules
| GSI-prespec | GSI-FRS | Lund | York | Euroball | Köln | Total | Needed | missing
VME crate | 4 |  | 1 |  |  |  | 5 | 5 | 0
RIO4 | 1 |  | 2 |  |  |  | 3 | 3 | 0
RIO3 | 2 | [5 empty] | 2 | 2 | 0
TRIVIA | 3 |  | 2 |  |  |  | 5 | 5 | 0
v785 | 9 |  | 3 |  | 4 | 4 | 16 | 18 | 2 | one or two from land
v775 |  |  | 1 |  |  |  | 1 | 1 | 0
v767 | 1 |  |  | 2 |  |  | 3 | 3 | 0
v1290 | 1 | 1 | 1 | 1 |  |  | 4 | 4 | 0
SIS mod | 5 | [5 empty] | 5 | 5 | 0
TITRIS | 1 | [5 empty] | 1 | 1 | 0
STM16+ | 14 |  | 4 | 8 |  |  | 26
MSCF-16 |  |  | 4 |  |  |  | 4
STM 16 nRC | [5 empty] | 6 | 6
Shapers | [6 empty] | 36 | 36 | 0
MVH-HV | 2 |  | 1 | 1 |  |  | 4 | 4 | 0
MNV pre-pow. |  |  | 1 |  |  |  | 1 | 1 | 0
RC unit | 2 |  | 1 |  |  |  | 3 | 3 | 0
CFD 812 | 11 |  | 1 | 1 |  |  | 13 | 13 | 0
Note on C8: spietri: includes 6 from TASCA and one from scanner Crate!!! An other one from henning crate possible??
Note on E8: spietri: 2 from Tasca and one from Dirk

## whowhennice
|  | LYCCA | HECTOR (background) | PRESPEC set-up | AGATA (background) | MUSIC (high rate) | TPC (test) | mechanics | particle detectors | gamma detectors | EDAQ | FRS settings | online/nearline analysis
[24 empty] | september | [19 empty] | october
Name | Institute | Special interest/expertise | [11 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 17 | 18 | 19 | 20
Mike Bentley | York | bar: 7 to 10; september 15 to september 24
Nara Singh | York | x | bar: 6 to september 11
Lianne Scruton | York | bar: 6 to september 11; september 15 to september 24
Douglas DiJulio | Lund | bar: september 17 to september 22
Pavel Golubev | Lund | bar: 7 to september 11; september 15 to september 20
Joakim Cederkall | Lund
Robert Hoischen | Lund | x | bar: 7 to september 11; september 15 to september 20
Dirk Rudolph | Lund | bar: september 21 to september 24
Andreas Wendt | Köln | x | bar: 7 to 10; september 15 to september 23
Peter Reiter | Köln
Jan Taprogge | Köln | x | bar: september 15 to september 23
Zsolt Podolyak | Surrey | [10 empty] | x
Fabio Schiru | Surrey | bar: 6 to september 18
Pieter Doornenbal | Riken | [10 empty] | x
Jurek Grebosz | bar: september 28 to october 20
Branislav Sitar | Bratislava | [5 empty] | x | bar: september 13 to september 23
Victor Stoica | KVI |  |  |  |  | x | bar: september 17 to september 23
Peter Schakel | KVI |  |  |  |  | x | bar: september 17 to september 23
Franco Camera | Milano |  | x | bar: 9 to september 11
Sergio Brambilla | bar: 9 to september 11
Oliver Wieland | bar: 10 to september 13
Miroslav Danchev | Univ. Sofia
Marek Pfützner | Univ. Warsaw
Ivan Kojouharov | bar: september 15 to september 22
HI/DESPEC week | bar: october 5 to october 10
Zakopane | bar: 1 to 5

## whowhen
| May May |  |  |  | June June June June June June June June June | [29 empty] | July | [7 empty] | notes
| week 18 | week 19 | week 20 | week 21 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Lund
Douglas DiJulio | bar: June June June June June June June June June 22 to July 2
Pavek Golubev | bar: June June June June June June June June June 24 to July 8
Joakim Cederkall | bar: June June June June June June June June June 24 to June June June June June June June June June 30
Robet Hioschen | bar: May May week 20 to May May week 21; June June June June June June June June June 16 to June June June June June June June June June 18; June June June June June June June June June 24 to July 8
Dirk Rudolf | bar: June June June June June June June June June 26 to July 8
University of Sofia
Miroslav Danchen
Kalin Gladnishki
Student
York
Nara Singh
Lian Scruton
Mike Bentley
Surrey
Zsolt Podolyak | bar: July 3 to July 8
Fabio Schiru (diamond)
KVI
V.Stoika | bar: June June June June June June June June June 28 to July 8
P Saekel | bar: June June June June June June June June June 27 to June June June June June June June June June 30